## Quote
SANRIA Limited
3080, Olcott Steet, Santa Clara
CA 95054
www.sanriaengineering.com ¦ www.icadengineering.com
Project Proposal
[6 empty] | Date: | 2016-04-08
Project Name: |  | Unvy. Of Montana - Football Scoreboard, Missoula
Customer Name: |  | STEWART-AMOS Steel, Inc.
4400 Paxton Street, Harrisburg, PA 17111, Attention: Curt Zeigler (717-901-2353)
Scope of Work: | 1. | Structural Steel Detailing including Embeds, Columns, Beams, Bracings, Trusses, Frames, Deck angles, connectors for joists, checkered plates, edge angles, deck angles
| 2. | Miscellaneous Steel: Hand rails, Caged Ladders with swing gate; Gratings ;
( we need to have details of standards for the misc. steel from customer)
Exclusions: | 1. | All Joist and Metal Decking
| 2. | Materials of architectural importance, Gage Metals, Metal Deck/Roof decking/studs,
Support frames for LED, Auxillary boards; Stairs & rails; Connection design;
Price: |  | Main & Misc. Steel Structure
|  | Detailing |  | US $ 4,500/- lump sum
Deliverables: | 1. | Advanced Bill of Materials (ABM)
| 2. | Erection Plans
| 3. | Detailed Shop Drawings
| 4. | Part Drawings
| 5. | NC output files from TEKLA Structures
Schedule: |  | OFA by 3 weeks from the RFC receiving date
Inputs: | 1. | Ready for Construction Contract Drawings
| 2. | Project Specifications
| 3. | Customer shop standards
Terms:
| 1. | The project start date is effective upon receipt of contract drawings, specifications and Purchase Order in the name of SANRIA Limited, USA.
| 2. | Our project delivery schedule is based on Customer's timely responses to our RFIs. Any delay in RFI answers will delay our deliverables
| 3. | The project delivery schedule is also dependent on the number of sequences and size of each sequence
| 4. | Customer is required to review approved shop drawings before fabrication
| 5. | All changes and rework in the project will be billed extra. Change orders will be submitted for such changes.
| 6. | 95% of PO value is billed upon release of drawings for approval and balance 5% after release of drawings for fabrication. Progress billing will be submitted for projects exceeding 6 weeks schedule
| 7. | All invoices are due net 30 days from the date of invoice
| 8. | On site customer meetings and onsite support are chargable
| 9. | We shall not be contractually obligated to any party other than Customer, regardless of Customer agreements/contracts with third parties
| 10. | All disputes are resolved through arbitration in a mutually agreed location and the local laws shall apply in the event of any disputes
Contact: |  | USA |  |  | INDIA
|  | Mahesh Nagarajaiah |  |  | Anand Mirji
|  | President |  |  | Head of Global Sales
|  | p: +1 408 620 5878 x1015 |  |  | p: +1 408 620 5878 x1010
|  | m: +1 510 996 2022 |  |  | m: +91 99456 56500
|  | mn@icadengineering.com |  |  | anand.mirji@icadengineering.com